## Sheet1
Task | Predecessor | Succsessor | Duration | Description | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critcal Task?
Start | [] | ['A.1'] |  |  | 0 | 0 | 0 | 0 | TRUE
A.1 | ['Start'] | ['A.2', 'A.3', 'A.4'] |  | Building Design | 0 | 12 | 0 | 12 | TRUE
A.2 | ['A.1'] | ['B.1'] |  | Electrical Design | 12 | 18 | 12 | 18 | TRUE
A.3 | ['A.1'] | ['B.1'] |  | Plumbing Design | 12 | 18 | 12 | 18 | TRUE
A.4 | ['A.1'] | ['B.1'] |  | Fire System Design | 12 | 16 | 14 | 18 | FALSE
B.1 | ['A.2', 'A.3', 'A.4'] | ['B.2', 'B.3', 'B.4'] |  | Signing Project Contract | 18 | 22 | 18 | 22 | TRUE
B.2 | ['B.1'] | ['C.1'] |  | Project Permit | 22 | 28 | 24 | 30 | FALSE
B.3 | ['B.1'] | ['C.1'] |  | Electrical Permit | 22 | 30 | 22 | 30 | TRUE
B.4 | ['B.1'] | ['C.1'] |  | Plumbing Permit | 22 | 28 | 24 | 30 | FALSE
C.1 | ['B.2', 'B.3', 'B.4'] | ['C.2', 'C.3'] |  | Installation of Mobilization Building | 30 | 38 | 30 | 38 | TRUE
C.2 | ['C.1'] | ['D.1'] |  | Road Work | 38 | 44 | 38 | 44 | TRUE
C.3 | ['C.1'] | ['D.1'] |  | Fence Work | 38 | 42 | 40 | 44 | FALSE
D.1 | ['C.2', 'C.3'] | ['D.2'] |  | Clearing and Grubbing | 44 | 48 | 44 | 48 | TRUE
D.2 | ['D.1'] | ['D.3'] |  | Excavation | 48 | 60 | 48 | 60 | TRUE
D.3 | ['D.2'] | ['E.1'] |  | Filling | 60 | 80 | 60 | 80 | TRUE
E.1 | ['D.3'] | ['E.2', 'E.3'] |  | Pile | 80 | 98 | 80 | 98 | TRUE
E.2 | ['E.1'] | ['F.1'] |  | Concrete | 98 | 118 | 108 | 128 | FALSE
E.3 | ['E.1'] | ['F.1'] |  | Raft Foundation | 98 | 128 | 98 | 128 | TRUE
F.1 | ['E.2', 'E.3'] | ['F.2', 'F.3', 'F.4', 'F.5'] |  | Column and Curtain Wall | 128 | 144 | 128 | 144 | TRUE
F.2 | ['F.1'] | ['G.1'] |  | Slab | 144 | 150 | 150 | 156 | FALSE
F.3 | ['F.1'] | ['G.1'] |  | Slab Insulation | 144 | 156 | 144 | 156 | TRUE
F.4 | ['F.1'] | ['G.1'] |  | Masonry | 144 | 150 | 150 | 156 | FALSE
F.5 | ['F.1'] | ['G.1'] |  | Upper Slab | 144 | 148 | 152 | 156 | FALSE
G.1 | ['F.2', 'F.3', 'F.4', 'F.5'] | ['G.2', 'G.3', 'G.4', 'G.5'] |  | Column and Curtain Wall | 156 | 164 | 156 | 164 | TRUE
G.2 | ['G.1'] | ['H.1'] |  | Slab | 164 | 172 | 164 | 172 | TRUE
G.3 | ['G.1'] | ['H.1'] |  | Slab Insulation | 164 | 170 | 166 | 172 | FALSE
G.4 | ['G.1'] | ['H.1'] |  | Masonry | 164 | 168 | 168 | 172 | FALSE
G.5 | ['G.1'] | ['H.1'] |  | Upper Slab | 164 | 168 | 168 | 172 | FALSE
H.1 | ['G.2', 'G.3', 'G.4', 'G.5'] | ['H.2', 'H.3'] |  | Roof Beam Installation | 172 | 180 | 172 | 180 | TRUE
H.2 | ['H.1'] | ['I.1', 'I.2', 'I.3'] |  | Roof Installation | 180 | 188 | 180 | 188 | TRUE
H.3 | ['H.1'] | ['I.1', 'I.2', 'I.3'] |  | Roof Isolation | 180 | 184 | 184 | 188 | FALSE
I.1 | ['H.2', 'H.3'] | ['J.2', 'J.3'] |  | Installation of Electric | 188 | 200 | 188 | 200 | TRUE
I.2 | ['H.2', 'H.3'] | ['J.2', 'J.3'] |  | Installation of Plumbing | 188 | 196 | 192 | 200 | FALSE
I.3 | ['H.2', 'H.3'] | ['J.2', 'J.3'] |  | Installation of Fire System | 188 | 192 | 196 | 200 | FALSE
J.2 | ['I.1', 'I.2', 'I.3'] | ['J.1'] |  | Interior Brick Wall | 200 | 232 | 200 | 232 | TRUE
J.3 | ['I.1', 'I.2', 'I.3'] | ['J.1'] |  | Exterior Brick Wall | 200 | 228 | 204 | 232 | FALSE
J.1 | ['J.2', 'J.3'] | ['Gate'] |  | Drywall | 232 | 250 | 232 | 250 | TRUE
Gate | ['J.1'] | ['K.1'] |  | Gate | 250 | 250 | 250 | 250 | TRUE
K.1 | ['Gate'] | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] |  | Plaster (ext-int) | 250 | 268 | 250 | 268 | TRUE
L.1 | ['K.1'] | ['M.1'] |  | Travertine Coating | 268 | 296 | 268 | 296 | TRUE
L.2 | ['K.1'] | ['M.1'] |  | Marble Coating | 268 | 284 | 280 | 296 | FALSE
L.3 | ['K.1'] | ['M.1'] |  | Tile Mosaic Coating | 268 | 276 | 288 | 296 | FALSE
L.4 | ['K.1'] | ['M.1'] |  | Ceramic Coating | 268 | 272 | 292 | 296 | FALSE
L.5 | ['K.1'] | ['M.1'] |  | Epoxy | 268 | 272 | 292 | 296 | FALSE
L.6 | ['K.1'] | ['M.1'] |  | Suspended Ceiling Cover | 268 | 284 | 280 | 296 | FALSE
L.7 | ['K.1'] | ['M.1'] |  | Outer Wall Covering | 268 | 292 | 272 | 296 | FALSE
M.1 | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] | ['M.2', 'M.3', 'M.4'] |  | Fenestration Installation | 296 | 302 | 296 | 302 | TRUE
M.2 | ['M.1'] | ['N.1'] |  | Wood Work | 302 | 314 | 302 | 314 | TRUE
M.3 | ['M.1'] | ['N.1'] |  | Aluminium Joinery | 302 | 310 | 306 | 314 | FALSE
M.4 | ['M.1'] | ['N.1'] |  | Metal Joinery | 302 | 308 | 308 | 314 | FALSE
N.1 | ['M.2', 'M.3', 'M.4'] | ['N.2'] |  | Interior Paint | 314 | 322 | 314 | 322 | TRUE
N.2 | ['N.1'] | ['O.1', 'O.2', 'O.3'] |  | Exterior Paint | 322 | 340 | 322 | 340 | TRUE
O.1 | ['N.2'] | ['O.4', 'O.5'] |  | Ventilation System | 340 | 344 | 348 | 352 | FALSE
O.2 | ['N.2'] | ['O.4', 'O.5'] |  | Clean-Waste Water | 340 | 352 | 340 | 352 | TRUE
O.3 | ['N.2'] | ['O.4', 'O.5'] |  | Rain Water | 340 | 344 | 348 | 352 | FALSE
O.4 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] |  | Mechanical Automation | 352 | 356 | 352 | 356 | TRUE
O.5 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] |  | Mechanical Electric Work | 352 | 356 | 352 | 356 | TRUE
P.1 | ['O.4', 'O.5'] | ['Q.1'] |  | Fire Protection System | 356 | 360 | 358 | 362 | FALSE
P.2 | ['O.4', 'O.5'] | ['Q.1'] |  | Fire Detection System | 356 | 362 | 356 | 362 | TRUE
P.3 | ['O.4', 'O.5'] | ['Q.1'] |  | Security Lighting | 356 | 360 | 358 | 362 | FALSE
Q.1 | ['P.1', 'P.2', 'P.3'] | ['Q.2'] |  | Cleaning | 362 | 366 | 362 | 366 | TRUE
Q.2 | ['Q.1'] | ['Q.3'] |  | Final Control | 366 | 370 | 366 | 370 | TRUE
Q.3 | ['Q.2'] | ['Completion'] |  | Delivery | 370 | 371 | 370 | 371 | TRUE
Completion | ['Q.3'] | [] |  |  | 371 | 371 | 371 | 371 | TRUE