## Sheet1
Task | Predecessor | Succsessor | Duration | Description | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critcal Task?
Start | [] | ['A.1'] | 0 |  | 0 | 0 | 0 | 0 | TRUE
A.1 | ['Start'] | ['A.2', 'A.3', 'A.4'] | 18 | Building Design | 0 | 18 | 0 | 18 | TRUE
A.2 | ['A.1'] | ['B.1'] | 9 | Electrical Design | 18 | 27 | 18 | 27 | TRUE
A.3 | ['A.1'] | ['B.1'] | 9 | Plumbing Design | 18 | 27 | 18 | 27 | TRUE
A.4 | ['A.1'] | ['B.1'] | 6 | Fire System Design | 18 | 24 | 21 | 27 | FALSE
B.1 | ['A.2', 'A.3', 'A.4'] | ['B.2', 'B.3', 'B.4'] | 6 | Signing Project Contract | 27 | 33 | 27 | 33 | TRUE
B.2 | ['B.1'] | ['C.1'] | 9 | Project Permit | 33 | 42 | 36 | 45 | FALSE
B.3 | ['B.1'] | ['C.1'] | 12 | Electrical Permit | 33 | 45 | 33 | 45 | TRUE
B.4 | ['B.1'] | ['C.1'] | 9 | Plumbing Permit | 33 | 42 | 36 | 45 | FALSE
C.1 | ['B.2', 'B.3', 'B.4'] | ['C.2', 'C.3'] | 12 | Installation of Mobilization Building | 45 | 57 | 45 | 57 | TRUE
C.2 | ['C.1'] | ['D.1'] | 9 | Road Work | 57 | 66 | 57 | 66 | TRUE
C.3 | ['C.1'] | ['D.1'] | 6 | Fence Work | 57 | 63 | 60 | 66 | FALSE
D.1 | ['C.2', 'C.3'] | ['D.2'] | 6 | Clearing and Grubbing | 66 | 72 | 66 | 72 | TRUE
D.2 | ['D.1'] | ['D.3'] | 18 | Excavation | 72 | 90 | 72 | 90 | TRUE
D.3 | ['D.2'] | ['E.1'] | 30 | Filling | 90 | 120 | 90 | 120 | TRUE
E.1 | ['D.3'] | ['E.2', 'E.3'] | 27 | Pile | 120 | 147 | 120 | 147 | TRUE
E.2 | ['E.1'] | ['F.1'] | 30 | Concrete | 147 | 177 | 162 | 192 | FALSE
E.3 | ['E.1'] | ['F.1'] | 45 | Raft Foundation | 147 | 192 | 147 | 192 | TRUE
F.1 | ['E.2', 'E.3'] | ['F.2', 'F.3', 'F.4', 'F.5'] | 24 | Column and Curtain Wall | 192 | 216 | 192 | 216 | TRUE
F.2 | ['F.1'] | ['G.1'] | 9 | Slab | 216 | 225 | 225 | 234 | FALSE
F.3 | ['F.1'] | ['G.1'] | 18 | Slab Insulation | 216 | 234 | 216 | 234 | TRUE
F.4 | ['F.1'] | ['G.1'] | 9 | Masonry | 216 | 225 | 225 | 234 | FALSE
F.5 | ['F.1'] | ['G.1'] | 6 | Upper Slab | 216 | 222 | 228 | 234 | FALSE
G.1 | ['F.2', 'F.3', 'F.4', 'F.5'] | ['G.2', 'G.3', 'G.4', 'G.5'] | 12 | Column and Curtain Wall | 234 | 246 | 234 | 246 | TRUE
G.2 | ['G.1'] | ['H.1'] | 12 | Slab | 246 | 258 | 246 | 258 | TRUE
G.3 | ['G.1'] | ['H.1'] | 9 | Slab Insulation | 246 | 255 | 249 | 258 | FALSE
G.4 | ['G.1'] | ['H.1'] | 6 | Masonry | 246 | 252 | 252 | 258 | FALSE
G.5 | ['G.1'] | ['H.1'] | 6 | Upper Slab | 246 | 252 | 252 | 258 | FALSE
H.1 | ['G.2', 'G.3', 'G.4', 'G.5'] | ['H.2', 'H.3'] | 12 | Roof Beam Installation | 258 | 270 | 258 | 270 | TRUE
H.2 | ['H.1'] | ['I.1', 'I.2', 'I.3'] | 12 | Roof Installation | 270 | 282 | 270 | 282 | TRUE
H.3 | ['H.1'] | ['I.1', 'I.2', 'I.3'] | 6 | Roof Isolation | 270 | 276 | 276 | 282 | FALSE
I.1 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 18 | Installation of Electric | 282 | 300 | 282 | 300 | TRUE
I.2 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 12 | Installation of Plumbing | 282 | 294 | 288 | 300 | FALSE
I.3 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 6 | Installation of Fire System | 282 | 288 | 294 | 300 | FALSE
J.2 | ['I.1', 'I.2', 'I.3'] | ['J.1'] | 48 | Interior Brick Wall | 300 | 348 | 300 | 348 | TRUE
J.3 | ['I.1', 'I.2', 'I.3'] | ['J.1'] | 42 | Exterior Brick Wall | 300 | 342 | 306 | 348 | FALSE
J.1 | ['J.2', 'J.3'] | ['K.1'] | 27 | Drywall | 348 | 375 | 348 | 375 | TRUE
K.1 | ['J.1'] | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] | 27 | Plaster (ext-int) | 375 | 402 | 375 | 402 | TRUE
L.1 | ['K.1'] | ['M.1'] | 42 | Travertine Coating | 402 | 444 | 402 | 444 | TRUE
L.2 | ['K.1'] | ['M.1'] | 24 | Marble Coating | 402 | 426 | 420 | 444 | FALSE
L.3 | ['K.1'] | ['M.1'] | 12 | Tile Mosaic Coating | 402 | 414 | 432 | 444 | FALSE
L.4 | ['K.1'] | ['M.1'] | 6 | Ceramic Coating | 402 | 408 | 438 | 444 | FALSE
L.5 | ['K.1'] | ['M.1'] | 6 | Epoxy | 402 | 408 | 438 | 444 | FALSE
L.6 | ['K.1'] | ['M.1'] | 24 | Suspended Ceiling Cover | 402 | 426 | 420 | 444 | FALSE
L.7 | ['K.1'] | ['M.1'] | 36 | Outer Wall Covering | 402 | 438 | 408 | 444 | FALSE
M.1 | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] | ['M.2', 'M.3', 'M.4'] | 9 | Fenestration Installation | 444 | 453 | 444 | 453 | TRUE
M.2 | ['M.1'] | ['N.1'] | 18 | Wood Work | 453 | 471 | 453 | 471 | TRUE
M.3 | ['M.1'] | ['N.1'] | 12 | Aluminium Joinery | 453 | 465 | 459 | 471 | FALSE
M.4 | ['M.1'] | ['N.1'] | 9 | Metal Joinery | 453 | 462 | 462 | 471 | FALSE
N.1 | ['M.2', 'M.3', 'M.4'] | ['N.2'] | 12 | Interior Paint | 471 | 483 | 471 | 483 | TRUE
N.2 | ['N.1'] | ['O.1', 'O.2', 'O.3'] | 27 | Exterior Paint | 483 | 510 | 483 | 510 | TRUE
O.1 | ['N.2'] | ['O.4', 'O.5'] | 6 | Ventilation System | 510 | 516 | 522 | 528 | FALSE
O.2 | ['N.2'] | ['O.4', 'O.5'] | 18 | Clean-Waste Water | 510 | 528 | 510 | 528 | TRUE
O.3 | ['N.2'] | ['O.4', 'O.5'] | 6 | Rain Water | 510 | 516 | 522 | 528 | FALSE
O.4 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] | 6 | Mechanical Automation | 528 | 534 | 528 | 534 | TRUE
O.5 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] | 6 | Mechanical Electric Work | 528 | 534 | 528 | 534 | TRUE
P.1 | ['O.4', 'O.5'] | ['Q.1'] | 6 | Fire Protection System | 534 | 540 | 537 | 543 | FALSE
P.2 | ['O.4', 'O.5'] | ['Q.1'] | 9 | Fire Detection System | 534 | 543 | 534 | 543 | TRUE
P.3 | ['O.4', 'O.5'] | ['Q.1'] | 6 | Security Lighting | 534 | 540 | 537 | 543 | FALSE
Q.1 | ['P.1', 'P.2', 'P.3'] | ['Q.2'] | 6 | Cleaning | 543 | 549 | 543 | 549 | TRUE
Q.2 | ['Q.1'] | ['Q.3'] | 6 | Final Control | 549 | 555 | 549 | 555 | TRUE
Q.3 | ['Q.2'] | ['Completion'] | 1 | Delivery | 555 | 556 | 555 | 556 | TRUE
Completion | ['Q.3'] | [] | 0 |  | 556 | 556 | 556 | 556 | TRUE