## Sheet1
Task | Predecessor | Succsessor | Duration | Description | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critcal Task?
Start | [] | ['A.1'] | 0 |  | 0 | 0 | 0 | 0 | TRUE
A.1 | ['Start'] | ['A.2', 'A.3', 'A.4'] | 6 | Building Design | 0 | 6 | 0 | 6 | TRUE
A.2 | ['A.1'] | ['B.1'] | 3 | Electrical Design | 6 | 9 | 6 | 9 | TRUE
A.3 | ['A.1'] | ['B.1'] | 3 | Plumbing Design | 6 | 9 | 6 | 9 | TRUE
A.4 | ['A.1'] | ['B.1'] | 2 | Fire System Design | 6 | 8 | 7 | 9 | FALSE
B.1 | ['A.2', 'A.3', 'A.4'] | ['B.2', 'B.3', 'B.4'] | 2 | Signing Project Contract | 9 | 11 | 9 | 11 | TRUE
B.2 | ['B.1'] | ['C.1'] | 3 | Project Permit | 11 | 14 | 12 | 15 | FALSE
B.3 | ['B.1'] | ['C.1'] | 4 | Electrical Permit | 11 | 15 | 11 | 15 | TRUE
B.4 | ['B.1'] | ['C.1'] | 3 | Plumbing Permit | 11 | 14 | 12 | 15 | FALSE
C.1 | ['B.2', 'B.3', 'B.4'] | ['C.2', 'C.3'] | 4 | Installation of Mobilization Building | 15 | 19 | 15 | 19 | TRUE
C.2 | ['C.1'] | ['D.1'] | 3 | Road Work | 19 | 22 | 19 | 22 | TRUE
C.3 | ['C.1'] | ['D.1'] | 2 | Fence Work | 19 | 21 | 20 | 22 | FALSE
D.1 | ['C.2', 'C.3'] | ['D.2'] | 2 | Clearing and Grubbing | 22 | 24 | 22 | 24 | TRUE
D.2 | ['D.1'] | ['D.3'] | 6 | Excavation | 24 | 30 | 24 | 30 | TRUE
D.3 | ['D.2'] | ['E.1'] | 10 | Filling | 30 | 40 | 30 | 40 | TRUE
E.1 | ['D.3'] | ['E.2', 'E.3'] | 9 | Pile | 40 | 49 | 40 | 49 | TRUE
E.2 | ['E.1'] | ['F.1'] | 10 | Concrete | 49 | 59 | 54 | 64 | FALSE
E.3 | ['E.1'] | ['F.1'] | 15 | Raft Foundation | 49 | 64 | 49 | 64 | TRUE
F.1 | ['E.2', 'E.3'] | ['F.2', 'F.3', 'F.4', 'F.5'] | 8 | Column and Curtain Wall | 64 | 72 | 64 | 72 | TRUE
F.2 | ['F.1'] | ['G.1'] | 3 | Slab | 72 | 75 | 75 | 78 | FALSE
F.3 | ['F.1'] | ['G.1'] | 6 | Slab Insulation | 72 | 78 | 72 | 78 | TRUE
F.4 | ['F.1'] | ['G.1'] | 3 | Masonry | 72 | 75 | 75 | 78 | FALSE
F.5 | ['F.1'] | ['G.1'] | 2 | Upper Slab | 72 | 74 | 76 | 78 | FALSE
G.1 | ['F.2', 'F.3', 'F.4', 'F.5'] | ['G.2', 'G.3', 'G.4', 'G.5'] | 4 | Column and Curtain Wall | 78 | 82 | 78 | 82 | TRUE
G.2 | ['G.1'] | ['H.1'] | 4 | Slab | 82 | 86 | 82 | 86 | TRUE
G.3 | ['G.1'] | ['H.1'] | 3 | Slab Insulation | 82 | 85 | 83 | 86 | FALSE
G.4 | ['G.1'] | ['H.1'] | 2 | Masonry | 82 | 84 | 84 | 86 | FALSE
G.5 | ['G.1'] | ['H.1'] | 2 | Upper Slab | 82 | 84 | 84 | 86 | FALSE
H.1 | ['G.2', 'G.3', 'G.4', 'G.5'] | ['H.2', 'H.3'] | 4 | Roof Beam Installation | 86 | 90 | 86 | 90 | TRUE
H.2 | ['H.1'] | ['I.1', 'I.2', 'I.3'] | 4 | Roof Installation | 90 | 94 | 90 | 94 | TRUE
H.3 | ['H.1'] | ['I.1', 'I.2', 'I.3'] | 2 | Roof Isolation | 90 | 92 | 92 | 94 | FALSE
I.1 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 6 | Installation of Electric | 94 | 100 | 94 | 100 | TRUE
I.2 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 4 | Installation of Plumbing | 94 | 98 | 96 | 100 | FALSE
I.3 | ['H.2', 'H.3'] | ['J.2', 'J.3'] | 2 | Installation of Fire System | 94 | 96 | 98 | 100 | FALSE
J.2 | ['I.1', 'I.2', 'I.3'] | ['J.1'] | 16 | Interior Brick Wall | 100 | 116 | 100 | 116 | TRUE
J.3 | ['I.1', 'I.2', 'I.3'] | ['J.1'] | 14 | Exterior Brick Wall | 100 | 114 | 102 | 116 | FALSE
J.1 | ['J.2', 'J.3'] | ['K.1'] | 9 | Drywall | 116 | 125 | 116 | 125 | TRUE
K.1 | ['J.1'] | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] | 9 | Plaster (ext-int) | 125 | 134 | 125 | 134 | TRUE
L.1 | ['K.1'] | ['M.1'] | 14 | Travertine Coating | 134 | 148 | 134 | 148 | TRUE
L.2 | ['K.1'] | ['M.1'] | 8 | Marble Coating | 134 | 142 | 140 | 148 | FALSE
L.3 | ['K.1'] | ['M.1'] | 4 | Tile Mosaic Coating | 134 | 138 | 144 | 148 | FALSE
L.4 | ['K.1'] | ['M.1'] | 2 | Ceramic Coating | 134 | 136 | 146 | 148 | FALSE
L.5 | ['K.1'] | ['M.1'] | 2 | Epoxy | 134 | 136 | 146 | 148 | FALSE
L.6 | ['K.1'] | ['M.1'] | 8 | Suspended Ceiling Cover | 134 | 142 | 140 | 148 | FALSE
L.7 | ['K.1'] | ['M.1'] | 12 | Outer Wall Covering | 134 | 146 | 136 | 148 | FALSE
M.1 | ['L.1', 'L.2', 'L.3', 'L.4', 'L.5', 'L.6', 'L.7'] | ['M.2', 'M.3', 'M.4'] | 3 | Fenestration Installation | 148 | 151 | 148 | 151 | TRUE
M.2 | ['M.1'] | ['N.1'] | 6 | Wood Work | 151 | 157 | 151 | 157 | TRUE
M.3 | ['M.1'] | ['N.1'] | 4 | Aluminium Joinery | 151 | 155 | 153 | 157 | FALSE
M.4 | ['M.1'] | ['N.1'] | 3 | Metal Joinery | 151 | 154 | 154 | 157 | FALSE
N.1 | ['M.2', 'M.3', 'M.4'] | ['N.2'] | 4 | Interior Paint | 157 | 161 | 157 | 161 | TRUE
N.2 | ['N.1'] | ['O.1', 'O.2', 'O.3'] | 9 | Exterior Paint | 161 | 170 | 161 | 170 | TRUE
O.1 | ['N.2'] | ['O.4', 'O.5'] | 2 | Ventilation System | 170 | 172 | 174 | 176 | FALSE
O.2 | ['N.2'] | ['O.4', 'O.5'] | 6 | Clean-Waste Water | 170 | 176 | 170 | 176 | TRUE
O.3 | ['N.2'] | ['O.4', 'O.5'] | 2 | Rain Water | 170 | 172 | 174 | 176 | FALSE
O.4 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] | 2 | Mechanical Automation | 176 | 178 | 176 | 178 | TRUE
O.5 | ['O.1', 'O.2', 'O.3'] | ['P.1', 'P.2', 'P.3'] | 2 | Mechanical Electric Work | 176 | 178 | 176 | 178 | TRUE
P.1 | ['O.4', 'O.5'] | ['Q.1'] | 2 | Fire Protection System | 178 | 180 | 179 | 181 | FALSE
P.2 | ['O.4', 'O.5'] | ['Q.1'] | 3 | Fire Detection System | 178 | 181 | 178 | 181 | TRUE
P.3 | ['O.4', 'O.5'] | ['Q.1'] | 2 | Security Lighting | 178 | 180 | 179 | 181 | FALSE
Q.1 | ['P.1', 'P.2', 'P.3'] | ['Q.2'] | 2 | Cleaning | 181 | 183 | 181 | 183 | TRUE
Q.2 | ['Q.1'] | ['Q.3'] | 2 | Final Control | 183 | 185 | 183 | 185 | TRUE
Q.3 | ['Q.2'] | ['Completion'] | 1 | Delivery | 185 | 186 | 185 | 186 | TRUE
Completion | ['Q.3'] | [] | 0 |  | 186 | 186 | 186 | 186 | TRUE