## Sheet1
Task | Predecessor | Succsessor | Duration | Description | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critcal Task?
Start | [] | ['A', 'B'] | 0 |  | 0 | 0 | 0 | 0 | TRUE
A | ['Start'] | ['C', 'D', 'E'] | 6 | Agreement of the owner | 0 | 6 | 0 | 6 | TRUE
B | ['Start'] | ['D'] | 4 | Preparation of the ground | 0 | 4 | 6 | 10 | FALSE
C | ['A'] | ['F'] | 3 | Order of materials | 6 | 9 | 6 | 9 | TRUE
D | ['A', 'B'] | ['G'] | 3 | Excavation | 6 | 9 | 10 | 13 | FALSE
E | ['A'] | ['H'] | 4 | Order of doors and windows | 6 | 10 | 7 | 11 | FALSE
F | ['C'] | ['G'] | 4 | Delivery of materials | 9 | 13 | 9 | 13 | TRUE
G | ['D', 'F'] | ['J'] | 4 | Concrete foundations | 13 | 17 | 13 | 17 | TRUE
H | ['E'] | ['K'] | 12 | Delivery of doors and windows | 10 | 22 | 11 | 23 | FALSE
J | ['G'] | ['K'] | 6 | Frame, roofs, walls | 17 | 23 | 17 | 23 | TRUE
K | ['H', 'J'] | ['End'] | 3 | Installation of doors and windows | 23 | 26 | 23 | 26 | TRUE
End | ['K'] | [] | 0 |  | 26 | 26 | 26 | 26 | TRUE