## Sheet1
Task | Predecessor | Succsessor | Duration | Description | Early Start Date | Early Completion Date | Late Start Date | Late Completion Date | Critcal Task?
Start | [] | ['A', 'B'] | 0 |  | 0 | 0 | 0 | 0 | TRUE
A | ['Start'] | ['C', 'D', 'E'] | 4 | Agreement of the owner | 0 | 4 | 0 | 4 | TRUE
B | ['Start'] | ['D'] | 2 | Preparation of the ground | 0 | 2 | 7 | 9 | FALSE
C | ['A'] | ['F'] | 1 | Order of materials | 4 | 5 | 7 | 8 | FALSE
D | ['A', 'B'] | ['G'] | 1 | Excavation | 4 | 5 | 9 | 10 | FALSE
E | ['A'] | ['H'] | 2 | Order of doors and windows | 4 | 6 | 4 | 6 | TRUE
F | ['C'] | ['G'] | 2 | Delivery of materials | 5 | 7 | 8 | 10 | FALSE
G | ['D', 'F'] | ['J'] | 2 | Concrete foundations | 7 | 9 | 10 | 12 | FALSE
H | ['E'] | ['K'] | 10 | Delivery of doors and windows | 6 | 16 | 6 | 16 | TRUE
J | ['G'] | ['K'] | 4 | Frame, roofs, walls | 9 | 13 | 12 | 16 | FALSE
K | ['H', 'J'] | ['End'] | 1 | Installation of doors and windows | 16 | 17 | 16 | 17 | TRUE
End | ['K'] | [] | 0 |  | 17 | 17 | 17 | 17 | TRUE